## Detailed status
Sprint task | Test case Id | Test case | Sub Levels | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed)
Adding crops to a plot | T_C_100 | Adding crops |  | High | Tester A | 2016-11-12 | Pass
| 100.1 |  | Adding cauliflower on empty plot | High |  | 2016-11-13 | Pass
| 100.2 |  | Cauliflower added to already cultivated plot | High |  | 2016-11-14 | Pass
Removing a crop from a plot | Id: T_C_102 | Removing crops |  | High | Tester A | 2016-11-15 | Pass
| 102.1 |  | Removing cauliflower from plot | High | Tester A | 2016-11-16 | Pass
| 102.2 |  | Empty plot selected for removing crops | High | Tester A | 2016-11-17 | Pass
Implementing the land selection option |  |  |  |  | Tester A
Tester A
Soil Selection | T_C_106 | Soil Selection |  | Medium | Tester A | 2016-11-20 | Pass
| 106.1 |  | selecting soil of currently selected plot | Medium | Tester A | 2016-11-21 | Pass
Water Selection | T_C_104 | Updating water resources |  | Medium | Tester A | 2016-11-22 | Pass
| 104.1 |  | Updating water resources to all cultivtaed crops | Medium | Tester A | 2016-11-23 | Pass
Fetilizer Selection | T_C_103 | Updating fertilizer to crops |  | Medium | Tester A | 2016-11-24 | Pass
| 103.1 |  | Updating water fertilizers to all cultivtaed crops | Medium | Tester A | 2016-11-25 | Pass
Selecting Start and End Dates | T_C_109 | Selecting start and end dates |  | High | Tester A | 2016-11-26 | Pass
| 109.1 |  | selecting start date and end date for simulation | High | Tester A | 2016-11-27 | Pass
| 109.2 |  | selecting end date less than 3 months | High | Tester A | 2016-11-28 | Pass
| 109.3 |  | slecting end date more than 3 years | High | Tester A | 2016-11-29 | Pass
Change PlotSize | 109.1 | Change plotsize |  | Low | Tester A | 2016-11-29 | Pass
| 303.1 | Usability test | Guerilla Usability test | High | Tester A | 2016-12-06 | Pass
|  | Connect to database |  | High | Tester A | 2016-12-06 | Pass