## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 100
| Number of testers | 5
| Test cycle duration | 5 days
Status for
| Number of test cases planned | 20 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 18
| Number of test cases executed overall | 78
| Number of defects encountered today | 2
| Number of defect encountered so far | 10
| Number of critical defects- still open | 3
Overall status
| Number of test cases planned | 100
| Number of test cases executed | 78
| Pass Percentage of the defects | 98%
| Defects density | 2.5 per day
| Critical defects percentage | 20%

## Detailed status
Sprint task | Test case Id | Test case | Sub Levels | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed)
Adding crops to a plot | T_C_100 | Adding crops |  | High | Tester A | 2016-11-12 | Pass
| 100.1 |  | Adding cauliflower on empty plot | High |  | 2016-11-13 | Pass
| 100.2 |  | Cauliflower added to already cultivated plot | High |  | 2016-11-14 | Pass
Removing a crop from a plot | Id: T_C_102 | Removing crops |  | High | Tester A | 2016-11-15 | Pass
| 102.1 |  | Removing cauliflower from plot | High | Tester A | 2016-11-16 | Pass
| 102.2 |  | Empty plot selected for removing crops | High | Tester A | 2016-11-17 | Pass
Implementing the land selection option |  |  |  |  | Tester A
Tester A
Soil Selection | T_C_106 | Soil Selection |  | Medium | Tester A | 2016-11-20 | Pass
| 106.1 |  | selecting soil of currently selected plot | Medium | Tester A | 2016-11-21 | Pass
Water Selection | T_C_104 | Updating water resources |  | Medium | Tester A | 2016-11-22 | Pass
| 104.1 |  | Updating water resources to all cultivtaed crops | Medium | Tester A | 2016-11-23 | Pass
Fetilizer Selection | T_C_103 | Updating fertilizer to crops |  | Medium | Tester A | 2016-11-24 | Pass
| 103.1 |  | Updating water fertilizers to all cultivtaed crops | Medium | Tester A | 2016-11-25 | Pass
Selecting Start and End Dates | T_C_109 | Selecting start and end dates |  | High | Tester A | 2016-11-26 | Pass
| 109.1 |  | selecting start date and end date for simulation | High | Tester A | 2016-11-27 | Pass
| 109.2 |  | selecting end date less than 3 months | High | Tester A | 2016-11-28 | Pass
| 109.3 |  | slecting end date more than 3 years | High | Tester A | 2016-11-29 | Pass
Change PlotSize | 109.1 | Change plotsize |  | Low | Tester A | 2016-11-29 | Pass
| 303.1 | Usability test | Guerilla Usability test | High | Tester A | 2016-12-06 | Pass
|  | Connect to database |  | High | Tester A | 2016-12-06 | Pass

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
1028 | Cannot add car make, 404 error on clicking the link | 1. Login to the site using the admin credentials 2. Click on the "Car Make Management" menu option from the left side navigation 3. The list of the makes of the cars available will be displayed 4. There will also be a link "Add new car make" present on the top(header) of the list 5. Click on the link Expected result: The page where the admin can enter a new make for the car should be displayed Actual Result: A 404 error causes the system to crash. The site has to be relaunched to recover from this state. | 1- High | Open | Tester X | Dev representative