## Sheet1
Task Id | Task Name | Story | Priority | Status | Story Points | Start Date | End Date | Assigned To
| Sprint 1 | No | High | In Progress | 165 | Monday, November 21,2016 | Saturday, November 26,2016
101 | Defining Classes, Methods and Variables, and database table constructure | no | Medium | In Progress | 30 |  |  | All
102 | Basic GUI Design | No | Low | In Progress | 15
103 | Final GUI Design | No | High | In Progress | 45 |  |  | All
104 | Populating the database with crop, regional and weather details. | No | Medium | In Progress | 60 |  |  | All
105 | Demo | No | High | Not Started | 15 |  |  | All
| Sprint 2 | Yes | High | Not Started | 125 | Sunday, November 27,2016 | Sunday, December 4,2016
201 | Adding Crops to a Plot | Yes | High | Not Started | 15 |  |  | Tsank & Zisis
202 | Removing a crop(s) from a plot | Yes | High | Not Started | 30 |  |  | Richard & Raima
203 | Implementing the land selection option | Yes | High | Not Started | 15 |  |  | Khan
204 | Soil Selection | Yes | Medium | Not Started | 5 |  |  | Richard
205 | Water Selection | Yes | Medium | Not Started | 5 |  |  | Mike
206 | Fetilizer Selection | Yes | Medium | Not Started | 5 |  |  | Mke
207 | Selecting Start and End Dates | Yes | High | Not Started | 15 |  |  | Mikle
208 | Changing Plot Size | Yes | Low | Not Started | 5 |  |  | Mike
209 | Test Report | Yes | Medium | Not Started | 15 |  |  | All
210 | Demo | No | High | Not Started | 15 |  |  | All
| Sprint 3 | Yes | High | Not Started | 190 | Monday, December 12, 2016 | Sprint 3 Friday 23, 2016
301 | Implementing the run simulation | Yes | High | Not Started | 100 |  |  | All
302 | Save Simulation | Yes | High | Not Started | 30 |  |  | Richard & Raima
303 | Exit Application | Yes | Medium | Not Started | 5 |  |  | Khan
304 | Load Application | Yes | High | Not Started | 15 |  |  | Tsank & Zisis
305 | Implementing ther Information Panel | Yes | High | Not Started | 10 |  |  | Mike
306 | Test Report | Yes | Medium | Not Started | 15 |  |  | All
307 | Demo | No | High | Not Started | 15 |  |  | All
| Sprint 4 | Yes | High | Not Started | 165 | Monday, Janurary 9, 2017 | Sunday, Janurary 15,2017
401 | Generating Report | Yes | High | Not Started | 75 |  |  | All
402 | Task Report | Yes | Medium | Not Started | 60 |  |  | All
403 | Demo | No | High | Not Started | 30 |  |  | All
Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started